## Sign Up (By test cases)
Estimation Functionality "Sign Up"
| Description | Quantity | Time (min) | Time (hours) | Time (days)
1. | Writing test case | 1 | 10
2. | Writing all test cases | 93 | 930
3. | Requirements analysis | - | 240
4. | Execution a test case | 1 | 7
5. | Execution test cases: | 372 | 2604
5.1. | all test cases | 93
5.2. | Quantity of times depending on functionality | 3
5.3. | Quantity of environments (www.prepear.com) | 1
6. | Risks & other activities (illness, build failed, some tests not counted, development delays, etc.) | 20% | 706.8
7. | Total* |  | 4480.8 | 74.68 | 9.335
Total= (time to write one test cases*quantity of all test cases) + (time to execute one test cases*quantity of execution of all test cases)+ ( time to analyze requirements ) + time risks

## Search (By test cases)
Estimation Functionality "Search"
| Description | Quantity | Time (min) | Time (hours) | Time (days)
1. | Writing test case | 1 | 10
2. | Writing all test cases | 23 | 230
3. | Requirements analysis | - | 240
4. | Execution test case | 1 | 5
5. | Execution test cases: | 92 | 460
5.1. | all test cases | 23
5.2. | Quantity of times depending on functionality | 3
5.3. | Quantity of environments (www.prepear.com) | 1
6. | Risks & other activities (illness, build failed, some tests not counted, development delays, etc.) | 20% | 138
7. | Total* |  | 1068 | 17.8 | 2.225
Total= (time to write one test cases*quantity of all test cases) + (time to execute one test cases*quantity of execution of all test cases)+ ( time to analyze requirements ) + time risks

## Sign Up (3-Point Estimation)
Estimation Functionality "Sign Up"
Task Testing | Optimistic, h | Most Likely, h | Pessimistic, h
Requirements clarification | 2 | 5 | 12
Test Outlines writing (quantity =93) | 3 | 8 | 15
Test Data creation | 0.5 | 2 | 4
Smoke test | 1 | 4 | 8
Feature full test (Critical Path, Extended) | 2.5 | 6 | 14
Test Result Report writing | 0.5 | 2 | 5
SUM | 9.5 | 27 | 58
TOTAL (ET)* | 29.25
ET (Expected time)= (Sum Optimistic+ 4*Sum Most Likely+Sum Pessimistic)/6 =29,25 hours~3,7 days

## Search (3-Point Estimation)
Estimation Functionality "Sign Up"
Task Testing | Optimistic, h | Most Likely, h | Pessimistic, h
Requirements clarification | 0.5 | 1.5 | 5
Test Outlines writing (quantity=23) | 1 | 3 | 6
Test Data creation | 0.2 | 1 | 3
Smoke test | 0.5 | 1.5 | 3
Feature full test (Critical Path, Extended) | 1 | 2.5 | 5
Test Result Report writing | 0.1 | 1.5 | 3
SUM | 3.3 | 11 | 25
TOTAL (ET)* | 12.05
ET (Expected time)= (Sum Optimistic+ 4*Sum Most Likely+Sum Pessimistic)/6 =12,05 hours~1,5 days